## ProjectList
Upper San Gabriel Valley Municipal Water District
Local Resources Inventory
Metropolitan's 2015 Integrated Water Resources Plan and Regional Urban Water Management Plan
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
ID | Water Type | Project Name | Status | Project Terms |  |  |  |  | Project Use |  | Project Location and System Integration |  | Project Finance |  | Project Barriers/Needs | History |  |  | Forecast
MWD Tracking | 1. GWR - GW Recovery 2. REC - Recycled 3. SWD - Desalination | Project/Sub Project | 1. Existing 2. Under Construction 3. Full Design & Appropriated Funds 4. Planning (EIR/EIS Certified) 5. Feasibility 6. Conceptual | Project receiving MWD funding? Recycled Water: - LRP/Non-LRP GW Recovery: - GRP/Non-GRP Seatwater Desal: - SDP/Non-SDP | Estimated Start of Operation | LRP Contract Expiration Date | Ultimate Yield (AFY) | Project Ramp-Up Period (Years Until Ultimate Yield) | 1. Potable Direct 2. Potable Indirect 3. Non-potable | 1. MI - Municipal & Industrial 2. AG - Agricultural 3. SWB - Seawater Barrier 4. GW - Groundwater Recharge | Address or Coordinates (Latitude and Longitude) | If integrating to MWD's system, specify point of connection | Total Capital Cost (2015 Dollars) | O&M Costs - $/AF (2015 Dollars) | Specify barriers that needed to be addressed to move the project forward (e.g., water quality, funding, public perception, system integration, permitting) | 2012 | 2013 | 2014 | 2015 | 2020 | 2025 | 2030 | 2035 | 2040
k272 | REC | City of Industry Regional Recycled Water System/City of Industry Regional Recycled Water Project - Suburban (93%) | Existing | LRP | 2011 | 2030 | 3032 |  | Non-potable | MI | [5 empty] | 269.7 | 561.9 | 426.2867
k279 | REC | Direct Reuse/Direct Reuse Project Phase IIA | Existing | LRP | 2006 | 2030 | 2258 |  | Non-potable | MI | [5 empty] | 1610.6 | 1594.3 | 1249.2433
k281 | REC | Direct Reuse/Direct Reuse, Phase I | Existing | Non-LRP | 2003 |  | 1000 |  | Non-potable | MI | [5 empty] | 1637.143 | 757.2479 | 898.1851
k275 | REC | Direct Reuse/Direct Reuse, Phase IIA Expansion/Rosemead Extension Project | Existing | Non-LRP | 2012 |  | 720 |  | Non-potable | MI | [7 empty] | 292.19
k418 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 2) | Existing | Non-LRP | 2012 |  | 360 |  | Non-potable | MI | [7 empty] | 124.26
k280 | REC | Los Angeles County Sanitation District Projects | Existing | Non-LRP | 1985 |  | 4375 |  | Non-potable | MI | [5 empty] | 3421.7817 | 4098.9998 | 3848.2994
k282 | REC | Norman's Nursery | Existing | Non-LRP | 1997 |  | 100 |  | Non-potable | MI | [5 empty] | 11.6556 | 0 | 2.0122
k277 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase I | Full Design & Appropriated Funds | Non-LRP | 2016 |  | 10000 |  | Potable Indirect | GW | DELETE - DUPLICATE OF k493
k493 | REC | Indirect Reuse Replenishment Project (IRRP) | Full Design & Appropriated Funds | Non-LRP | 2017 (revise to 2018) |  | 10000 |  | Non-potable (revise to Potable Indirect) | MI (Revise to GW)
k419 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 3) | Feasibility (Revise to Existing) | Non-LRP | 2012 |  | 310 |  | Non-potable | MI | ONLINE - COMPLETE
k420 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 4) | Feasibility (Revise to Existing) | Non-LRP | 2012 |  | 210 |  | Non-potable | MI | ONLINE - COMPLETE
k415 | REC | Direct Reuse/Direct Reuse, Future Extensions of the Recycled Water Program | Full Design & Appropriated Funds | Non-LRP (Revise to LRP) | 2016 |  | 500 (Revise to 130) |  | Non-potable | MI
k416 | REC | Direct Reuse/Direct Reuse, Phase I - Rose Hills Expansion | Full Design & Appropriated Funds | Non-LRP (Revise to LRP) | 2015 (revise to 2016) |  | 530 (Revise to 600) |  | Non-potable | MI
k417 | REC | Direct Reuse/Direct Reuse, Phase II - Satelite Treatment Plant | Conceptual | Non-LRP | 2016 (Revise to 2020) |  | 500 |  | Non-potable | MI
k278 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase II | Conceptual | Non-LRP | 2022 |  | 10000 |  | Potable Indirect | GW | DELETE - DUPLICATE OF k493
k182 | REC | Joint Water Pollution Control Plant (JWPCP) | Conceptual | Non-LRP | 2016 |  | 35000 |  | Non-potable | MI | DELETE, NOT AN UPPER DISTRICT
| REC | Miller Coors Direct Reuse and Groundwater Recharge Project | Feasibility | LRP | 2017 |  | 1000 |  | Non-potable | MI | NEW ENTRY
2010 IRP Planned Projects
| REC | Direct Reuse, Phase IIA Expansion/Rosemead Extension Project | Advanced Planning (EIR/EIS Certified) |  | 2020 |  | 1850 |  | Upper San Gabriel
| REC | Direct Reuse, Phase I Expansion | Conceptual |  | 2020 |  | 1200 |  | Upper San Gabriel
| REC | Direct Reuse, Phase IIB | Conceptual |  | 2020 |  | 3700 |  | Upper San Gabriel
| REC | Groundwater Reliability Improvement Project (GRIP), Phase I | Conceptual |  | 2020 |  | 9000 |  | Upper San Gabriel
| REC | Groundwater Reliability Improvement Project (GRIP), Phase II | Conceptual |  | 2020 |  | 16000 |  | Upper San Gabriel
| REC | Joint Water Purification Project | Conceptual |  | 2020 |  | 35000 |  | Upper San Gabriel
| REC | Direct Reuse, Phase III | Feasibility |  | 2018 |  | 7000 |  | Upper San Gabriel

## Step1
Upper San Gabriel Valley Municipal Water District
Local Resources Inventory
Metropolitan's 2015 Integrated Water Resources Plan and Regional Urban Water Management Plan
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
ID | Water Type | Project Name | Status | Project Terms |  |  |  |  | Project Use |  | Project Location and System Integration |  | Project Finance |  | Project Barriers/Needs | History |  |  | Forecast
MWD Tracking | 1. GWR - GW Recovery 2. REC - Recycled 3. SWD - Desalination | Project/Sub Project | 1. Existing 2. Under Construction 3. Full Design & Appropriated Funds 4. Planning (EIR/EIS Certified) 5. Feasibility 6. Conceptual | Project receiving MWD funding? Recycled Water: - LRP/Non-LRP GW Recovery: - GRP/Non-GRP Seatwater Desal: - SDP/Non-SDP | Estimated Start of Operation | LRP Contract Expiration Date | Ultimate Yield (AFY) | Project Ramp-Up Period (Years Until Ultimate Yield) | 1. Potable Direct 2. Potable Indirect 3. Non-potable | 1. MI - Municipal & Industrial 2. AG - Agricultural 3. SWB - Seawater Barrier 4. GW - Groundwater Recharge | Address or Coordinates (Latitude and Longitude) | If integrating to MWD's system, specify point of connection | Total Capital Cost (2015 Dollars) | O&M Costs - $/AF (2015 Dollars) | Specify barriers that needed to be addressed to move the project forward (e.g., water quality, funding, public perception, system integration, permitting) | 2012 | 2013 | 2014 | 2015 | 2020 | 2025 | 2030 | 2035 | 2040
[11 empty] | LRP | Start Yr | Yield | Status
k272 | REC | City of Industry Regional Recycled Water System/City of Industry Regional Recycled Water Project - Suburban (93%) | Existing | LRP | 2011 | 2030 | 3032 |  | Non-potable | MI | [5 empty] | 269.7 | 561.9 | 426.2867
k272 | REC | Upper San Gabriel Valley Municipal Water District | City of Industry Regional Recycled Water System | City of Industry Regional Recycled Water Project - Suburban (93%) | MI | LRP | 2011 | 2030 | Existing | 3032 | TRUE | TRUE | TRUE | TRUE | [31 empty] | 0.1 | 1.1 | 269.7 | 561.9 | 426.2867 | 465 | 601.3659 | 674.3753 | 747.3847 | 820.3941 | 893.4036 | 966.413 | 1039.4224 | 1112.4318 | 1185.4412 | 1258.4506 | 1331.46 | 1404.4695 | 1477.4789 | 1550.4883 | 1623.4977 | 1696.5071 | 1769.5165 | 1842.5259 | 1915.5354 | 1988.5448 | 2061.5542 | 2134.5636 | 2207.573 | 2280.5824 | 2353.5918 | 2426.6013 | 2499.6107 | 2572.6201 | 2645.6295 | 2718.6389 | 2791.6483 | 2864.6577 | 2937.6672 | 3010.6766 | 3032 | 64901.7221
k275 | REC | Direct Reuse/Direct Reuse, Phase IIA Expansion/Rosemead Extension Project | Existing | Non-LRP | 2012 |  | 720 |  | Non-potable | MI | [7 empty] | 292.19
k275 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase IIA Expansion/Rosemead Extension Project | MI | No | 2012 |  | Existing | 720 | FALSE | TRUE | TRUE | TRUE | [35 empty] | 292.19 | 380.736 | 421.8091 | 445.8354 | 462.8823 | 476.1049 | 486.9085 | 496.0429 | 503.9554 | 510.9347 | 517.178 | 522.8257 | 527.9816 | 532.7246 | 537.116 | 541.2042 | 545.0285 | 548.6209 | 552.0079 | 555.2117 | 558.2511 | 561.1422 | 563.8988 | 566.5328 | 569.0548 | 571.4737 | 573.7978 | 576.0341 | 578.1891 | 580.2685 | 582.2774 | 584.2203 | 586.1016 | 587.9251 | 589.694 | 591.4117 | 593.081 | 19378.4622
k279 | REC | Direct Reuse/Direct Reuse Project Phase IIA | Existing | LRP | 2006 | 2030 | 2258 |  | Non-potable | MI | [5 empty] | 1610.6 | 1594.3 | 1249.2433
k279 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse Project Phase IIA | MI | LRP | 2006 | 2030 | Existing | 2258 | TRUE | TRUE | TRUE | TRUE | [27 empty] | 271 | 1140.2 | 855 | 455.6 | 1350.8 | 1334.2 | 1610.6 | 1594.3 | 1249.2433 | 1570 | 1570 | 1664.8 | 1759.6 | 1854.4 | 1949.2 | 2044 | 2138.8 | 2233.6 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 77750.4
k280 | REC | Los Angeles County Sanitation District Projects | Existing | Non-LRP | 1985 |  | 4375 |  | Non-potable | MI | [5 empty] | 3421.7817 | 4098.9998 | 3848.2994
k280 | REC | Upper San Gabriel Valley Municipal Water District | Los Angeles County Sanitation District Projects | Los Angeles County Sanitation District Projects | MI | No | 1985 |  | Existing | 4375 | FALSE | TRUE | TRUE | TRUE | [6 empty] | 920 | 1846 | 1444 | 1395 | 1714 | 1373.9 | 659.7 | 371.9 | 385.6 | 417.555 | 937.49 | 1561 | 1646.487 | 2800.6171 | 3517.4344 | 3366.0343 | 3320.5135 | 3585.5399 | 3331.2171 | 3592.9837 | 3111.5924 | 3415.1969 | 4025.8936 | 3847.4683 | 3965.9519 | 3606.1233 | 3417.6449 | 3421.7817 | 4098.9998 | 3848.2994 | 3963.5199 | 4078.7403 | 4193.9608 | 4309.1813 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 156545.4023
k281 | REC | Direct Reuse/Direct Reuse, Phase I | Existing | Non-LRP | 2003 |  | 1000 |  | Non-potable | MI | [5 empty] | 1637.143 | 757.2479 | 898.1851
k281 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase I | MI | No | 2003 |  | Existing | 1000 | FALSE | TRUE | TRUE | TRUE | [24 empty] | 25.3771 | 43.1697 | 50.5751 | 313.5989 | 754.0625 | 680.8523 | 645.4389 | 572.5984 | 540.7441 | 1637.143 | 757.2479 | 898.1851 | 969.7249 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 35969.7249
k282 | REC | Norman's Nursery | Existing | Non-LRP | 1997 |  | 100 |  | Non-potable | MI | [5 empty] | 11.6556 | 0 | 2.0122
k282 | REC | Upper San Gabriel Valley Municipal Water District | Norman's Nursery | Norman's Nursery | MI | No | 1997 |  | Existing | 100 | FALSE | TRUE | TRUE | TRUE | [18 empty] | 59.5611 | 57.4243 | 75.0032 | 82.4663 | 70.9907 | 68.0834 | 70.3306 | 19.646 | 7.1163 | 45.6939 | 51.2936 | 51.9505 | 28.9839 | 29.6992 | 0.98818 | 11.6556 | 0 | 2.0122 | 2.0684 | 2.1246 | 2.1808 | 2.2371 | 2.2933 | 2.3495 | 2.4057 | 2.462 | 2.5182 | 2.5744 | 2.6306 | 2.6869 | 2.7431 | 2.7993 | 2.8555 | 2.9118 | 2.968 | 3.0242 | 3.0804 | 3.1367 | 3.1929 | 3.2491 | 3.3053 | 3.3616 | 3.4178 | 3.474 | 3.5302 | 3.5865 | 3.6427 | 3.6989 | 3.7551 | 3.8114 | 3.8676 | 3.9238 | 3.98 | 4.0363 | 109.8839
k415 | REC | Direct Reuse/Direct Reuse, Future Extensions of the Recycled Water Program | Full Design & Appropriated Funds | Non-LRP (Revise to LRP) | 2016 |  | 500 (Revise to 130) |  | Non-potable | MI
k415 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Future Extensions of the Recycled Water Program | MI | No | 2016 |  | Full Design & Appropriated Funds | 130 | FALSE | TRUE | FALSE | TRUE | [36 empty] | 0 | 68.744 | 76.16 | 80.4981 | 83.576 | 85.9634 | 87.914 | 89.5633 | 90.9919 | 92.2521 | 93.3794 | 94.3991 | 95.33 | 96.1864 | 96.9793 | 97.7174 | 98.4079 | 99.0565 | 99.6681 | 100.2466 | 100.7953 | 101.3173 | 101.8151 | 102.2907 | 102.746 | 103.1828 | 103.6024 | 104.0062 | 104.3953 | 104.7707 | 105.1334 | 105.4842 | 105.8239 | 106.1531 | 106.4725 | 106.7827
k416 | REC | Direct Reuse/Direct Reuse, Phase I - Rose Hills Expansion | Full Design & Appropriated Funds | Non-LRP (Revise to LRP) | 2015 (revise to 2016) |  | 530 (Revise to 600) |  | Non-potable | MI
k416 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase I - Rose Hills Expansion | MI | No | 2016 |  | Full Design & Appropriated Funds | 600 | FALSE | TRUE | FALSE | TRUE | [36 empty] | 0 | 68.744 | 76.16 | 80.4981 | 83.576 | 85.9634 | 87.914 | 89.5633 | 90.9919 | 92.2521 | 93.3794 | 94.3991 | 95.33 | 96.1864 | 96.9793 | 97.7174 | 98.4079 | 99.0565 | 99.6681 | 100.2466 | 100.7953 | 101.3173 | 101.8151 | 102.2907 | 102.746 | 103.1828 | 103.6024 | 104.0062 | 104.3953 | 104.7707 | 105.1334 | 105.4842 | 105.8239 | 106.1531 | 106.4725 | 106.7827
k417 | REC | Direct Reuse/Direct Reuse, Phase II - Satelite Treatment Plant | Conceptual | Non-LRP | 2016 (Revise to 2020) |  | 500 |  | Non-potable | MI
k417 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase II - Satelite Treatment Plant | MI | No | 2020 |  | Conceptual | 500 | FALSE | TRUE | TRUE | TRUE | [36 empty] | 0 | 0 | 0 | 0 | 0 | 264.4 | 292.923 | 309.6079 | 321.446 | 330.6284 | 338.1309 | 344.4742 | 349.969 | 354.8158 | 359.1514 | 363.0734 | 366.6539 | 369.9477 | 372.9972 | 375.8363 | 378.492 | 380.9867 | 383.3388 | 385.5637 | 387.6744 | 389.6821 | 391.5964 | 393.4256 | 395.1769 | 396.8567 | 398.4707 | 400.0237 | 401.5202 | 402.9642 | 404.3593 | 405.7086
k418 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 2) | Existing | Non-LRP | 2012 |  | 360 |  | Non-potable | MI | [7 empty] | 124.26
k418 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase IIB - Industry (Package 2) | MI | No | 2012 |  | Existing | 360 | FALSE | TRUE | TRUE | TRUE | [35 empty] | 124.26 | 190.368 | 210.9046 | 222.9177 | 231.4411 | 238.0524 | 243.4542 | 248.0214 | 251.9777 | 255.4674 | 258.589 | 261.4128 | 263.9908 | 266.3623 | 268.558 | 270.6021 | 272.5143 | 274.3104 | 276.0039 | 277.6058 | 279.1256 | 280.5711 | 281.9494 | 283.2664 | 284.5274 | 285.7369 | 286.8989 | 288.0171 | 289.0946 | 290.1342 | 291.1387 | 292.1102 | 293.0508 | 293.9625 | 294.847 | 295.7059 | 296.5405 | 9689.2311
k419 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 3) | Feasibility (Revise to Existing) | Non-LRP | 2012 |  | 310 |  | Non-potable | MI | ONLINE - COMPLETE
k419 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase IIB - Industry (Package 3) | MI | No | 2012 |  | Existing | 310 | FALSE | TRUE | TRUE | FALSE | [36 empty] | 199.2965 | 204.9896 | 209.6412 | 213.574 | 216.9808 | 219.9858 | 222.6739 | 225.1055 | 227.3254 | 229.3676 | 231.2583 | 233.0185 | 234.6651 | 236.2118 | 237.6701 | 239.0495 | 240.3581 | 241.6029 | 242.7898 | 243.9239 | 245.0097 | 246.0512 | 247.0518 | 248.0147 | 248.9425 | 249.8378 | 250.7027 | 251.5393 | 252.3493 | 253.1344 | 253.896 | 254.6356 | 255.3543 | 256.0533 | 256.7337 | 257.3964 | 8576.1909
k420 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 4) | Feasibility (Revise to Existing) | Non-LRP | 2012 |  | 210 |  | Non-potable | MI | ONLINE - COMPLETE
k420 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase IIB - Industry (Package 4) | MI | No | 2012 |  | Existing | 210 | FALSE | TRUE | TRUE | FALSE | [36 empty] | 135.0073 | 138.8639 | 142.015 | 144.6792 | 146.987 | 149.0226 | 150.8436 | 152.4908 | 153.9946 | 155.378 | 156.6588 | 157.8512 | 158.9667 | 160.0144 | 161.0023 | 161.9367 | 162.8232 | 163.6665 | 164.4705 | 165.2387 | 165.9743 | 166.6798 | 167.3577 | 168.0099 | 168.6385 | 169.245 | 169.8309 | 170.3976 | 170.9463 | 171.4781 | 171.9941 | 172.4951 | 172.982 | 173.4555 | 173.9164 | 174.3653 | 5809.6777
k493 | REC | Indirect Reuse Replenishment Project (IRRP) | Full Design & Appropriated Funds | Non-LRP | 2017 (revise to 2018) |  | 10000 |  | Non-potable (revise to Potable Indirect) | MI (Revise to GW)
k493 | REC | Upper San Gabriel Valley Municipal Water District | Indirect Reuse Replenishment Project (IRRP) | Indirect Reuse Replenishment Project (IRRP) | MI | No | 2018 |  | Full Design & Appropriated Funds | 10000 | FALSE | TRUE | TRUE | TRUE | [36 empty] | 0 | 0 | 0 | 378 | 606 | 834 | 1062 | 1290 | 1518 | 1746 | 1974 | 2202 | 2430 | 2658 | 2886 | 3114 | 3342 | 3570 | 3798 | 4026 | 4254 | 4482 | 4710 | 4938 | 5166 | 5394 | 5622 | 5850 | 6078 | 6306 | 6534 | 6762 | 6990 | 7218 | 7446 | 7674
New | REC | Upper San Gabriel Valley Municipal Water District | Miller Coors Direct Reuse and Groundwater Recharge Project |  | MI | LRP | 2017 |  | Feasibility | 1000 | [42 empty] | 528.8 | 585.846 | 619.2158 | 642.892 | 661.2567 | 676.2618 | 688.9484 | 699.938 | 709.6316 | 718.3028 | 726.1468 | 733.3078 | 739.8953 | 745.9944 | 751.6725 | 756.9841 | 761.9735 | 766.6776 | 771.1273 | 775.3488 | 779.3642 | 783.1928 | 786.8512 | 790.3538 | 793.7135 | 796.9413 | 800.0474 | 803.0404 | 805.9284 | 808.7185 | 811.4171 | 814.0301 | 816.5626 | 819.0195
| REC | Miller Coors Direct Reuse and Groundwater Recharge Project | Feasibility | LRP | 2017 |  | 1000 |  | Non-potable | MI | TRUE | FALSE | FALSE | FALSE
k344 | REC | Upper San Gabriel Valley Municipal Water District | City of Industry Regional Recycled Water System | City of Industry Regional Recycled Water Project - Suburban (93%) | MI | LRPx | 2030 |  | Not Existing | 3032 | [76 empty] | 0
k350 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse Project Phase IIA | MI | LRPx | 2030 |  | Not Existing | 2258 | [76 empty] | 0
Deleted
k277 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase I | Full Design & Appropriated Funds | Non-LRP | 2016 |  | 10000 |  | Potable Indirect | GW | DELETE - DUPLICATE OF k493
k278 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase II | Conceptual | Non-LRP | 2022 |  | 10000 |  | Potable Indirect | GW | DELETE - DUPLICATE OF k493
k182 | REC | Joint Water Pollution Control Plant (JWPCP) | Conceptual | Non-LRP | 2016 |  | 35000 |  | Non-potable | MI | DELETE, NOT AN UPPER DISTRICT
k182 | REC | Upper San Gabriel Valley Municipal Water District | Joint Water Pollution Control Plant (JWPCP) | Joint Water Pollution Control Plant (JWPCP) | MI | No | 2016 |  | Conceptual | 35000 | [40 empty] | 0 | 1323 | 2121 | 2919 | 3717 | 4515 | 5313 | 6111 | 6909 | 7707 | 8505 | 9303 | 10101 | 10899 | 11697 | 12495 | 13293 | 14091 | 14889 | 15687 | 16485 | 17283 | 18081 | 18879 | 19677 | 20475 | 21273 | 22071 | 22869 | 23667 | 24465 | 25263 | 26061 | 26859 | 27657 | 28455
2010 IRP Planned Projects
| REC | Direct Reuse, Phase IIA Expansion/Rosemead Extension Project | Advanced Planning (EIR/EIS Certified) |  | 2020 |  | 1850 |  | Upper San Gabriel
| REC | Direct Reuse, Phase I Expansion | Conceptual |  | 2020 |  | 1200 |  | Upper San Gabriel
| REC | Direct Reuse, Phase IIB | Conceptual |  | 2020 |  | 3700 |  | Upper San Gabriel
| REC | Groundwater Reliability Improvement Project (GRIP), Phase I | Conceptual |  | 2020 |  | 9000 |  | Upper San Gabriel
| REC | Groundwater Reliability Improvement Project (GRIP), Phase II | Conceptual |  | 2020 |  | 16000 |  | Upper San Gabriel
| REC | Joint Water Purification Project | Conceptual |  | 2020 |  | 35000 |  | Upper San Gabriel
| REC | Direct Reuse, Phase III | Feasibility |  | 2018 |  | 7000 |  | Upper San Gabriel

## Step2
Upper San Gabriel Valley Municipal Water District
Local Resources Inventory
Metropolitan's 2015 Integrated Water Resources Plan and Regional Urban Water Management Plan
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
ID | Water Type | Project Name | Status | Project Terms |  |  |  |  | Project Use |  | Project Location and System Integration |  | Project Finance |  | Project Barriers/Needs | History |  |  | Forecast
MWD Tracking | 1. GWR - GW Recovery 2. REC - Recycled 3. SWD - Desalination | Project/Sub Project | 1. Existing 2. Under Construction 3. Full Design & Appropriated Funds 4. Planning (EIR/EIS Certified) 5. Feasibility 6. Conceptual | Project receiving MWD funding? Recycled Water: - LRP/Non-LRP GW Recovery: - GRP/Non-GRP Seatwater Desal: - SDP/Non-SDP | Estimated Start of Operation | LRP Contract Expiration Date | Ultimate Yield (AFY) | Project Ramp-Up Period (Years Until Ultimate Yield) | 1. Potable Direct 2. Potable Indirect 3. Non-potable | 1. MI - Municipal & Industrial 2. AG - Agricultural 3. SWB - Seawater Barrier 4. GW - Groundwater Recharge | Address or Coordinates (Latitude and Longitude) | If integrating to MWD's system, specify point of connection | Total Capital Cost (2015 Dollars) | O&M Costs - $/AF (2015 Dollars) | Specify barriers that needed to be addressed to move the project forward (e.g., water quality, funding, public perception, system integration, permitting) | 2012 | 2013 | 2014 | 2015 | 2020 | 2025 | 2030 | 2035 | 2040
[11 empty] | LRP | Start Yr | Yield | Status
k272 | REC | Upper San Gabriel Valley Municipal Water District | City of Industry Regional Recycled Water System | City of Industry Regional Recycled Water Project - Suburban (93%) | MI | LRP | 2011 | 2030 | Existing | 3032 | #REF! | #REF! | #REF! | #REF! | [31 empty] | 0.1 | 1.1 | 269.7 | 561.9 | 426.2867 | 465 | 601.3659 | 674.3753 | 747.3847 | 820.3941 | 893.4036 | 966.413 | 1039.4224 | 1112.4318 | 1185.4412 | 1258.4506 | 1331.46 | 1404.4695 | 1477.4789 | 1550.4883 | 1623.4977 | 1696.5071 | 1769.5165 | 1842.5259 | 1915.5354 | 1988.5448 | 2061.5542 | 2134.5636 | 2207.573 | 2280.5824 | 2353.5918 | 2426.6013 | 2499.6107 | 2572.6201 | 2645.6295 | 2718.6389 | 2791.6483 | 2864.6577 | 2937.6672 | 3010.6766 | 3032 | 64901.7221
k275 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase IIA Expansion/Rosemead Extension Project | MI | No | 2012 |  | Existing | 720 | #REF! | #REF! | #REF! | #REF! | [35 empty] | 292.19 | 380.736 | 421.8091 | 445.8354 | 462.8823 | 476.1049 | 486.9085 | 496.0429 | 503.9554 | 510.9347 | 517.178 | 522.8257 | 527.9816 | 532.7246 | 537.116 | 541.2042 | 545.0285 | 548.6209 | 552.0079 | 555.2117 | 558.2511 | 561.1422 | 563.8988 | 566.5328 | 569.0548 | 571.4737 | 573.7978 | 576.0341 | 578.1891 | 580.2685 | 582.2774 | 584.2203 | 586.1016 | 587.9251 | 589.694 | 591.4117 | 593.081 | 19378.4622
k279 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse Project Phase IIA | MI | LRP | 2006 | 2030 | Existing | 2258 | #REF! | #REF! | #REF! | #REF! | [27 empty] | 271 | 1140.2 | 855 | 455.6 | 1350.8 | 1334.2 | 1610.6 | 1594.3 | 1249.2433 | 1570 | 1570 | 1664.8 | 1759.6 | 1854.4 | 1949.2 | 2044 | 2138.8 | 2233.6 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 2258 | 77750.4
k280 | REC | Upper San Gabriel Valley Municipal Water District | Los Angeles County Sanitation District Projects | Los Angeles County Sanitation District Projects | MI | No | 1985 |  | Existing | 4375 | #REF! | #REF! | #REF! | #REF! | [6 empty] | 920 | 1846 | 1444 | 1395 | 1714 | 1373.9 | 659.7 | 371.9 | 385.6 | 417.555 | 937.49 | 1561 | 1646.487 | 2800.6171 | 3517.4344 | 3366.0343 | 3320.5135 | 3585.5399 | 3331.2171 | 3592.9837 | 3111.5924 | 3415.1969 | 4025.8936 | 3847.4683 | 3965.9519 | 3606.1233 | 3417.6449 | 3421.7817 | 4098.9998 | 3848.2994 | 3963.5199 | 4078.7403 | 4193.9608 | 4309.1813 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 4375 | 156545.4023
k281 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase I | MI | No | 2003 |  | Existing | 1000 | #REF! | #REF! | #REF! | #REF! | [24 empty] | 25.3771 | 43.1697 | 50.5751 | 313.5989 | 754.0625 | 680.8523 | 645.4389 | 572.5984 | 540.7441 | 1637.143 | 757.2479 | 898.1851 | 969.7249 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 35969.7249
k282 | REC | Upper San Gabriel Valley Municipal Water District | Norman's Nursery | Norman's Nursery | MI | No | 1997 |  | Existing | 100 | #REF! | #REF! | #REF! | #REF! | [18 empty] | 59.5611 | 57.4243 | 75.0032 | 82.4663 | 70.9907 | 68.0834 | 70.3306 | 19.646 | 7.1163 | 45.6939 | 51.2936 | 51.9505 | 28.9839 | 29.6992 | 0.98818 | 11.6556 | 0 | 2.0122 | 2.0684 | 2.1246 | 2.1808 | 2.2371 | 2.2933 | 2.3495 | 2.4057 | 2.462 | 2.5182 | 2.5744 | 2.6306 | 2.6869 | 2.7431 | 2.7993 | 2.8555 | 2.9118 | 2.968 | 3.0242 | 3.0804 | 3.1367 | 3.1929 | 3.2491 | 3.3053 | 3.3616 | 3.4178 | 3.474 | 3.5302 | 3.5865 | 3.6427 | 3.6989 | 3.7551 | 3.8114 | 3.8676 | 3.9238 | 3.98 | 4.0363 | 109.8839
k415 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Future Extensions of the Recycled Water Program | MI | No | 2016 |  | Full Design & Appropriated Funds | 130 | #REF! | #REF! | #REF! | #REF! | [36 empty] | 0 | 68.744 | 76.16 | 80.4981 | 83.576 | 85.9634 | 87.914 | 89.5633 | 90.9919 | 92.2521 | 93.3794 | 94.3991 | 95.33 | 96.1864 | 96.9793 | 97.7174 | 98.4079 | 99.0565 | 99.6681 | 100.2466 | 100.7953 | 101.3173 | 101.8151 | 102.2907 | 102.746 | 103.1828 | 103.6024 | 104.0062 | 104.3953 | 104.7707 | 105.1334 | 105.4842 | 105.8239 | 106.1531 | 106.4725 | 106.7827
k416 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase I - Rose Hills Expansion | MI | No | 2016 |  | Full Design & Appropriated Funds | 600 | #REF! | #REF! | #REF! | #REF! | [36 empty] | 0 | 68.744 | 76.16 | 80.4981 | 83.576 | 85.9634 | 87.914 | 89.5633 | 90.9919 | 92.2521 | 93.3794 | 94.3991 | 95.33 | 96.1864 | 96.9793 | 97.7174 | 98.4079 | 99.0565 | 99.6681 | 100.2466 | 100.7953 | 101.3173 | 101.8151 | 102.2907 | 102.746 | 103.1828 | 103.6024 | 104.0062 | 104.3953 | 104.7707 | 105.1334 | 105.4842 | 105.8239 | 106.1531 | 106.4725 | 106.7827
k417 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase II - Satelite Treatment Plant | MI | No | 2020 |  | Conceptual | 500 | #REF! | #REF! | #REF! | #REF! | [36 empty] | 0 | 0 | 0 | 0 | 0 | 264.4 | 292.923 | 309.6079 | 321.446 | 330.6284 | 338.1309 | 344.4742 | 349.969 | 354.8158 | 359.1514 | 363.0734 | 366.6539 | 369.9477 | 372.9972 | 375.8363 | 378.492 | 380.9867 | 383.3388 | 385.5637 | 387.6744 | 389.6821 | 391.5964 | 393.4256 | 395.1769 | 396.8567 | 398.4707 | 400.0237 | 401.5202 | 402.9642 | 404.3593 | 405.7086
k418 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase IIB - Industry (Package 2) | MI | No | 2012 |  | Existing | 360 | #REF! | #REF! | #REF! | #REF! | [35 empty] | 124.26 | 190.368 | 210.9046 | 222.9177 | 231.4411 | 238.0524 | 243.4542 | 248.0214 | 251.9777 | 255.4674 | 258.589 | 261.4128 | 263.9908 | 266.3623 | 268.558 | 270.6021 | 272.5143 | 274.3104 | 276.0039 | 277.6058 | 279.1256 | 280.5711 | 281.9494 | 283.2664 | 284.5274 | 285.7369 | 286.8989 | 288.0171 | 289.0946 | 290.1342 | 291.1387 | 292.1102 | 293.0508 | 293.9625 | 294.847 | 295.7059 | 296.5405 | 9689.2311
k419 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase IIB - Industry (Package 3) | MI | No | 2012 |  | Existing | 310 | #REF! | #REF! | #REF! | #REF! | [36 empty] | 199.2965 | 204.9896 | 209.6412 | 213.574 | 216.9808 | 219.9858 | 222.6739 | 225.1055 | 227.3254 | 229.3676 | 231.2583 | 233.0185 | 234.6651 | 236.2118 | 237.6701 | 239.0495 | 240.3581 | 241.6029 | 242.7898 | 243.9239 | 245.0097 | 246.0512 | 247.0518 | 248.0147 | 248.9425 | 249.8378 | 250.7027 | 251.5393 | 252.3493 | 253.1344 | 253.896 | 254.6356 | 255.3543 | 256.0533 | 256.7337 | 257.3964 | 8576.1909
k420 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse, Phase IIB - Industry (Package 4) | MI | No | 2012 |  | Existing | 210 | #REF! | #REF! | #REF! | #REF! | [36 empty] | 135.0073 | 138.8639 | 142.015 | 144.6792 | 146.987 | 149.0226 | 150.8436 | 152.4908 | 153.9946 | 155.378 | 156.6588 | 157.8512 | 158.9667 | 160.0144 | 161.0023 | 161.9367 | 162.8232 | 163.6665 | 164.4705 | 165.2387 | 165.9743 | 166.6798 | 167.3577 | 168.0099 | 168.6385 | 169.245 | 169.8309 | 170.3976 | 170.9463 | 171.4781 | 171.9941 | 172.4951 | 172.982 | 173.4555 | 173.9164 | 174.3653 | 5809.6777
k493 | REC | Upper San Gabriel Valley Municipal Water District | Indirect Reuse Replenishment Project (IRRP) | Indirect Reuse Replenishment Project (IRRP) | MI | No | 2018 |  | Full Design & Appropriated Funds | 10000 | #REF! | #REF! | #REF! | #REF! | [36 empty] | 0 | 0 | 0 | 378 | 606 | 834 | 1062 | 1290 | 1518 | 1746 | 1974 | 2202 | 2430 | 2658 | 2886 | 3114 | 3342 | 3570 | 3798 | 4026 | 4254 | 4482 | 4710 | 4938 | 5166 | 5394 | 5622 | 5850 | 6078 | 6306 | 6534 | 6762 | 6990 | 7218 | 7446 | 7674
New USG1 | REC | Upper San Gabriel Valley Municipal Water District | Miller Coors Direct Reuse and Groundwater Recharge Project |  | MI | LRP | 2017 |  | Feasibility | 1000 | [42 empty] | 528.8 | 585.846 | 619.2158 | 642.892 | 661.2567 | 676.2618 | 688.9484 | 699.938 | 709.6316 | 718.3028 | 726.1468 | 733.3078 | 739.8953 | 745.9944 | 751.6725 | 756.9841 | 761.9735 | 766.6776 | 771.1273 | 775.3488 | 779.3642 | 783.1928 | 786.8512 | 790.3538 | 793.7135 | 796.9413 | 800.0474 | 803.0404 | 805.9284 | 808.7185 | 811.4171 | 814.0301 | 816.5626 | 819.0195
k344 | REC | Upper San Gabriel Valley Municipal Water District | City of Industry Regional Recycled Water System | City of Industry Regional Recycled Water Project - Suburban (93%) | MI | LRPx | 2030 |  | Not Existing | 3032 | [76 empty] | 0
k350 | REC | Upper San Gabriel Valley Municipal Water District | Direct Reuse | Direct Reuse Project Phase IIA | MI | LRPx | 2030 |  | Not Existing | 2258 | [76 empty] | 0
Deleted
k277 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase I | Full Design & Appropriated Funds | Non-LRP | 2016 |  | 10000 |  | Potable Indirect | GW | DELETE - DUPLICATE OF k493
k278 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase II | Conceptual | Non-LRP | 2022 |  | 10000 |  | Potable Indirect | GW | DELETE - DUPLICATE OF k493
k182 | REC | Joint Water Pollution Control Plant (JWPCP) | Conceptual | Non-LRP | 2016 |  | 35000 |  | Non-potable | MI | DELETE, NOT AN UPPER DISTRICT
k182 | REC | Upper San Gabriel Valley Municipal Water District | Joint Water Pollution Control Plant (JWPCP) | Joint Water Pollution Control Plant (JWPCP) | MI | No | 2016 |  | Conceptual | 35000 | [40 empty] | 0 | 1323 | 2121 | 2919 | 3717 | 4515 | 5313 | 6111 | 6909 | 7707 | 8505 | 9303 | 10101 | 10899 | 11697 | 12495 | 13293 | 14091 | 14889 | 15687 | 16485 | 17283 | 18081 | 18879 | 19677 | 20475 | 21273 | 22071 | 22869 | 23667 | 24465 | 25263 | 26061 | 26859 | 27657 | 28455
2010 IRP Planned Projects
| REC | Direct Reuse, Phase IIA Expansion/Rosemead Extension Project | Advanced Planning (EIR/EIS Certified) |  | 2020 |  | 1850 |  | Upper San Gabriel
| REC | Direct Reuse, Phase I Expansion | Conceptual |  | 2020 |  | 1200 |  | Upper San Gabriel
| REC | Direct Reuse, Phase IIB | Conceptual |  | 2020 |  | 3700 |  | Upper San Gabriel
| REC | Groundwater Reliability Improvement Project (GRIP), Phase I | Conceptual |  | 2020 |  | 9000 |  | Upper San Gabriel
| REC | Groundwater Reliability Improvement Project (GRIP), Phase II | Conceptual |  | 2020 |  | 16000 |  | Upper San Gabriel
| REC | Joint Water Purification Project | Conceptual |  | 2020 |  | 35000 |  | Upper San Gabriel
| REC | Direct Reuse, Phase III | Feasibility |  | 2018 |  | 7000 |  | Upper San Gabriel

## compared
Upper San Gabriel Valley Municipal Water District
Local Resources Inventory
Metropolitan's 2015 Integrated Water Resources Plan and Regional Urban Water Management Plan
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
ID | Water Type | Project Name | Status | Project Terms |  |  |  |  | Project Use |  | Project Location and System Integration |  | Project Finance |  | Project Barriers/Needs | History |  |  | Forecast
MWD Tracking | 1. GWR - GW Recovery 2. REC - Recycled 3. SWD - Desalination | Project/Sub Project | 1. Existing 2. Under Construction 3. Full Design & Appropriated Funds 4. Planning (EIR/EIS Certified) 5. Feasibility 6. Conceptual | Project receiving MWD funding? Recycled Water: - LRP/Non-LRP GW Recovery: - GRP/Non-GRP Seatwater Desal: - SDP/Non-SDP | Estimated Start of Operation | LRP Contract Expiration Date | Ultimate Yield (AFY) | Project Ramp-Up Period (Years Until Ultimate Yield) | 1. Potable Direct 2. Potable Indirect 3. Non-potable | 1. MI - Municipal & Industrial 2. AG - Agricultural 3. SWB - Seawater Barrier 4. GW - Groundwater Recharge | Address or Coordinates (Latitude and Longitude) | If integrating to MWD's system, specify point of connection | Total Capital Cost (2015 Dollars) | O&M Costs - $/AF (2015 Dollars) | Specify barriers that needed to be addressed to move the project forward (e.g., water quality, funding, public perception, system integration, permitting) | 2012 | 2013 | 2014 | 2015 | 2020 | 2025 | 2030 | 2035 | 2040
Compared
k182 | REC | Joint Water Pollution Control Plant (JWPCP) | Conceptual | Non-LRP | 2016 |  | 35000 |  | Non-potable | MI | DELETE, NOT AN UPPER DISTRICT
k182 | REC | Joint Water Pollution Control Plant (JWPCP) | Conceptual | Non-LRP | 2016 |  | 35000 |  | Non-potable | MI
k272 | REC | City of Industry Regional Recycled Water System/City of Industry Regional Recycled Water Project - Suburban (93%) | Existing | LRP | 2011 | 2030 | 3032 |  | Non-potable | MI | [5 empty] | 269.7 | 561.9 | 426.2867
k272 | REC | City of Industry Regional Recycled Water System/City of Industry Regional Recycled Water Project - Suburban (93%) | Existing | LRP | 2011 | 2030 | 3032 |  | Non-potable | MI | [5 empty] | 269.7 | 561.9 | 426.2867
k275 | REC | Direct Reuse/Direct Reuse, Phase IIA Expansion/Rosemead Extension Project | Existing | Non-LRP | 2012 |  | 720 |  | Non-potable | MI | [7 empty] | 292.19
k275 | REC | Direct Reuse/Direct Reuse, Phase IIA Expansion/Rosemead Extension Project | Existing | Non-LRP | 2012 |  | 720 |  | Non-potable | MI | [7 empty] | 292.19
k277 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase I | Full Design & Appropriated Funds | Non-LRP | 2016 |  | 10000 |  | Potable Indirect | GW | DELETE - DUPLICATE OF k493
k277 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase I | Full Design & Appropriated Funds | Non-LRP | 2016 |  | 10000 |  | Potable Indirect | GW
k278 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase II | Conceptual | Non-LRP | 2022 |  | 10000 |  | Potable Indirect | GW | DELETE - DUPLICATE OF k493
k278 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase II | Conceptual | Non-LRP | 2022 |  | 10000 |  | Potable Indirect | GW
k279 | REC | Direct Reuse/Direct Reuse Project Phase IIA | Existing | LRP | 2006 | 2030 | 2258 |  | Non-potable | MI | [5 empty] | 1610.6 | 1594.3 | 1249.2433
k279 | REC | Direct Reuse/Direct Reuse Project Phase IIA | Existing | LRP | 2006 | 2030 | 2258 |  | Non-potable | MI | [5 empty] | 1610.6 | 1594.3 | 1249.2433
k280 | REC | Los Angeles County Sanitation District Projects | Existing | Non-LRP | 1985 |  | 4375 |  | Non-potable | MI | [5 empty] | 3421.7817 | 4098.9998 | 3848.2994
k280 | REC | Los Angeles County Sanitation District Projects | Existing | Non-LRP | 1985 |  | 4375 |  | Non-potable | MI | [5 empty] | 3421.7817 | 4098.9998 | 3848.2994
k281 | REC | Direct Reuse/Direct Reuse, Phase I | Existing | Non-LRP | 2003 |  | 1000 |  | Non-potable | MI | [5 empty] | 1637.143 | 757.2479 | 898.1851
k281 | REC | Direct Reuse/Direct Reuse, Phase I | Existing | Non-LRP | 2003 |  | 1000 |  | Non-potable | MI | [5 empty] | 1637.143 | 757.2479 | 898.1851
k282 | REC | Norman's Nursery | Existing | Non-LRP | 1997 |  | 100 |  | Non-potable | MI | [5 empty] | 11.6556 | 0 | 2.0122
k282 | REC | Norman's Nursery | Existing | Non-LRP | 1997 |  | 100 |  | Non-potable | MI | [5 empty] | 11.6556 | 0 | 2.0122
k415 | REC | Direct Reuse/Direct Reuse, Future Extensions of the Recycled Water Program | Full Design & Appropriated Funds | Non-LRP (Revise to LRP) | 2016 |  | 500 (Revise to 130) |  | Non-potable | MI
k415 | REC | Direct Reuse/Direct Reuse, Future Extensions of the Recycled Water Program | Conceptual | Non-LRP | 2016 |  | 500 |  | Non-potable | MI
k416 | REC | Direct Reuse/Direct Reuse, Phase I - Rose Hills Expansion | Full Design & Appropriated Funds | Non-LRP (Revise to LRP) | 2015 (revise to 2016) |  | 530 (Revise to 600) |  | Non-potable | MI
k416 | REC | Direct Reuse/Direct Reuse, Phase I - Rose Hills Expansion | Conceptual | Non-LRP | 2015 |  | 530 |  | Non-potable | MI
k417 | REC | Direct Reuse/Direct Reuse, Phase II - Satelite Treatment Plant | Conceptual | Non-LRP | 2016 (Revise to 2020) |  | 500 |  | Non-potable | MI
k417 | REC | Direct Reuse/Direct Reuse, Phase II - Satelite Treatment Plant | Conceptual | Non-LRP | 2016 |  | 500 |  | Non-potable | MI
k418 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 2) | Existing | Non-LRP | 2012 |  | 360 |  | Non-potable | MI | [7 empty] | 124.26
k418 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 2) | Existing | Non-LRP | 2012 |  | 360 |  | Non-potable | MI | [7 empty] | 124.26
k419 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 3) | Feasibility (Revise to Existing) | Non-LRP | 2012 |  | 310 |  | Non-potable | MI | ONLINE - COMPLETE
k419 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 3) | Feasibility | Non-LRP | 2012 |  | 310 |  | Non-potable | MI
k420 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 4) | Feasibility (Revise to Existing) | Non-LRP | 2012 |  | 210 |  | Non-potable | MI | ONLINE - COMPLETE
k420 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 4) | Feasibility | Non-LRP | 2012 |  | 210 |  | Non-potable | MI
k493 | REC | Indirect Reuse Replenishment Project (IRRP) | Full Design & Appropriated Funds | Non-LRP | 2017 (revise to 2018) |  | 10000 |  | Non-potable (revise to Potable Indirect) | MI (Revise to GW)
k493 | REC | Indirect Reuse Replenishment Project (IRRP) | Full Design & Appropriated Funds | Non-LRP | 2017 |  | 10000 |  | Non-potable | MI
New | REC | Miller Coors Direct Reuse and Groundwater Recharge Project | Feasibility | LRP | 2017 |  | 1000 |  | Non-potable | MI | NEW ENTRY
Revised List
k272 | REC | City of Industry Regional Recycled Water System/City of Industry Regional Recycled Water Project - Suburban (93%) | Existing | LRP | 2011 | 2030 | 3032 |  | Non-potable | MI | [5 empty] | 269.7 | 561.9 | 426.2867
k275 | REC | Direct Reuse/Direct Reuse, Phase IIA Expansion/Rosemead Extension Project | Existing | Non-LRP | 2012 |  | 720 |  | Non-potable | MI | [7 empty] | 292.19
k279 | REC | Direct Reuse/Direct Reuse Project Phase IIA | Existing | LRP | 2006 | 2030 | 2258 |  | Non-potable | MI | [5 empty] | 1610.6 | 1594.3 | 1249.2433
k280 | REC | Los Angeles County Sanitation District Projects | Existing | Non-LRP | 1985 |  | 4375 |  | Non-potable | MI | [5 empty] | 3421.7817 | 4098.9998 | 3848.2994
k281 | REC | Direct Reuse/Direct Reuse, Phase I | Existing | Non-LRP | 2003 |  | 1000 |  | Non-potable | MI | [5 empty] | 1637.143 | 757.2479 | 898.1851
k282 | REC | Norman's Nursery | Existing | Non-LRP | 1997 |  | 100 |  | Non-potable | MI | [5 empty] | 11.6556 | 0 | 2.0122
k415 | REC | Direct Reuse/Direct Reuse, Future Extensions of the Recycled Water Program | Full Design & Appropriated Funds | LRP | 2016 |  | 130 |  | Non-potable | MI
k416 | REC | Direct Reuse/Direct Reuse, Phase I - Rose Hills Expansion | Full Design & Appropriated Funds | LRP | 2016 |  | 130 |  | Non-potable | MI
k417 | REC | Direct Reuse/Direct Reuse, Phase II - Satelite Treatment Plant | Conceptual | Non-LRP | 2020 |  | 500 |  | Non-potable | MI
k418 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 2) | Existing | Non-LRP | 2012 |  | 360 |  | Non-potable | MI | [7 empty] | 124.26
k419 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 3) | Existing | Non-LRP | 2012 |  | 310 |  | Non-potable | MI | ONLINE - COMPLETE
k420 | REC | Direct Reuse/Direct Reuse, Phase IIB - Industry (Package 4) | Existing | Non-LRP | 2012 |  | 210 |  | Non-potable | MI | ONLINE - COMPLETE
k493 | REC | Indirect Reuse Replenishment Project (IRRP) | Full Design & Appropriated Funds | Non-LRP | 2018 |  | 10000 |  | Potable Indirect | MI
New | REC | Miller Coors Direct Reuse and Groundwater Recharge Project | Feasibility | LRP | 2017 |  | 1000 |  | Non-potable | MI | NEW ENTRY
Deleted Projects
k182 | REC | Joint Water Pollution Control Plant (JWPCP) | Conceptual | Non-LRP | 2016 |  | 35000 |  | Non-potable | MI | DELETE, NOT AN UPPER DISTRICT
k182 | REC | Joint Water Pollution Control Plant (JWPCP) | Conceptual | Non-LRP | 2016 |  | 35000 |  | Non-potable | MI
k277 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase I | Full Design & Appropriated Funds | Non-LRP | 2016 |  | 10000 |  | Potable Indirect | GW | DELETE - DUPLICATE OF k493
k277 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase I | Full Design & Appropriated Funds | Non-LRP | 2016 |  | 10000 |  | Potable Indirect | GW
k278 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase II | Conceptual | Non-LRP | 2022 |  | 10000 |  | Potable Indirect | GW | DELETE - DUPLICATE OF k493
k278 | REC | Groundwater Reliability Improvement Project/Groundwater Reliability Improvement Project (GRIP), Phase II | Conceptual | Non-LRP | 2022 |  | 10000 |  | Potable Indirect | GW
Note on E52: Ti,Mike N: 6/9/2015 Revised to LRP by USGVMWD.
Note on H52: Ti,Mike N: 6/9/2015 Revised to 130 from 500 by USGVMWD.
Note on E53: Ti,Mike N: 6/9/2015 Revised to LRP by USGVMWD.
Note on H53: Ti,Mike N: 6/9/2015 Revised to 600 from 530 by USGVMWD.

## definitions
Local Resources Inventory
Definitions
The purpose of this survey is to update the inventory of all local resources projects in Metropolitan's service area. This Inventory List will be used in
planning activities for Metropolitan's 2015 Integrated Water Resources Plan Update and the 2015 Regional Urban Water Management Plan.
The attached Local Resources Inventory List contains all recycling, groundwater recovery, and seawater desalination projects we have in our records.
Please review and update each project accordingly. The table below shows detailed descriptions of the information requested.
Add any projects that are not on the list.
Please submit your completed list to Mike Ti (mike_ti@mwdh2o.com) by May 4, 2015.
Column Headings |  | Comments
ID | MWD Tracking | Metropolitan internal project tracking ID.
Water Type | 1. GWR - GW Recovery 2. REC - Recycled 3. SWD - Desalination | Specify water types: GWR - groundwater recovery, REC - water recycling, and SWD - seawater desalination. (Groundwater recovery projects extract and treat groundwater making it usable by removing chemicals and/or high level of salts.)
Project Name | Project/Sub Project | Verify project names. Projects that receive MWD funding should be consistent with the Local Resources Program agreement.
Status | 1. Existing 2. Under Construction 3. Full Design & Appropriated Funds 4. Planning (EIR/EIS Certified) 5. Feasibility 6. Conceptual | Specify or update project status. This will help us understand the phase of the project.
Project Terms | Project receiving MWD funding? Recycled Water: - LRP/Non-LRP GW Recovery: - GRP/Non-GRP Seawater Desal: - SDP/Non-SDP | For projects that receive MWD funding, please indicate the funding program: 1) LRP - Local Resources Program for water recycling; 2) GRP - Groundwater Recovery Program for treating contaminated groundwater; and 3) SDP - Seawater Desalination Program for treating seawater for potable use.
| Estimated Start of Operation | Specify the year when the project produces water.
| LRP Contract Expiration Date | For projects that receive MWD funding, please specify agreement expiration date.
| Ultimate Yield (AFY) | Specify the annual ultimate yield of the project.
| Project Ramp-Up Period (Years Until Ultimate Yield) | Specify the ramp-up period in order for the project to produce at ultimate yield.
Project Use | 1. Potable Direct 2. Potable Indirect 3. Non-potable | Specify the project use: 1) Potable Direct is product water suitable for direct potable uses; 2) Potable Indirect is product water that requires retention time in a groundwater basin or reservoir before it is extracted for potable uses; and 3) Non-potable is product water for not for potable uses.
| 1. MI - Municipal & Industrial 2. AG - Agricultural 3. SWB - Seawater Barrier 4. GW - Groundwater Recharge | Specify end of product water.
Project Location and System Integration | Address or Coordinates (Latitude and Longitude) | Specify address or coordinates of the project.
| If integrating to MWD's system, specify point of connection | If planned project requires integration with MWD's distribution system, specify the point of connection(s).
Project Finance | Total Capital Cost (2015 Dollars) | Specify the total capital cost in 2015 dollars.
| O&M Costs - $/AF (2015 Dollars) | Specify the cost per acre-foot in 2015 dollars.
Project Barriers/Needs | Specify barriers that needed to be addressed to move the project forward (e.g., water quality, funding, public perception, system integration, permitting) | Specify barriers that needed to be addressed to move the project forward (e.g., water quality, funding, public perception, system integration, permitting).
History | 2012 | Historical production tracked by Metropolitan.
2013
2014
Forecast | 2015 | Provide projected annual production in acre-feet.
2020
2025
2030
2035
2040
Source: H:\Projects\IRP Update 2015\Recycling\Local Project Inventory List (4-9-2013).xlsm